## Tasks
FPGA team roadmap v3 (draft)
Ref | Task | Workstream | Epic | Thread | Status | Owner | Estimate (days) | Depends on | Milestone | Notes | DAL | RAG
CH-01 | Team charter | Ways of Working | Team Charter | People | Done | Lead | 3 |  | M1 Foundations | Why we exist and how we work. |  | Green
CH-02 | Team charter | Ways of Working | Team Charter | People | WIP | Lead | 2d | CH-01 | M1 | Who decides what. Draft first, then review. |  | Amber
| Decide where we track tasks | Ways of Working | Planning & Tracking | Process | Not started | Avery | 1.5 | Team charter | M1
GIT-01 | GitLab group structure | Tooling & Automation | Git & GitLab | Tools | Complete | Blake | 2 |  | M1
GIT-02 | Repository layout | Tooling & Automation | Git & GitLab | Tools | In review | Blake | 4h | GIT-01; CH-02 | M1
CI-01 | CI runner with FPGA tools | Tooling & Automation | CI Pipelines | Tools | Blocked | Frankie | 5 | GIT-02, Licence server upgrade | M2 |  |  | Red
REV-01 | Code review checklist | Standards & Assurance | Reviews | Process | in progress | Drew | 3 | CH-02 | M1 |  | A/B
REV-02 | DAL A/B independent review | Standards & Assurance | Reviews | Process | Proposed |  |  | REV-01 | M3 |  | A, B

## Workstreams
ID | Workstream | Description | Map hint
WOW | Ways of Working | How we plan, track and share work. | west
TOOL | Tooling & Automation | Git, CI and scripted builds.
STD | Standards & Assurance | Standards, reviews and DO-254 tailoring. | nowhere

## Milestones
ID | Name | Target date | Exit criteria
M1 | Foundations | 2026-12-18 | Charter, tracking and repo layout agreed.
M2 | First project on the new way | 2027-03-31