## Project plan
ID | WBS | Name | Duration | Predecessors | % Complete | Resource Names
1 | 1 | Ways of Working
2 | 1.1 | Team Charter
3 | 1.1.1 | Write the charter | 3 days |  | 100% | Lead
4 | 1.1.2 | Roles and responsibilities |  | 3 | 50% | Lead[50%]
5 | 1.1.2.1 | Draft RACI | 1 day |  | 100%
6 | 1.1.2.2 | Review with the team | 1 day |  | 0%
7 | 2 | Tooling
8 | 2.1 | CI
9 | 2.1.1 | Runner | 5 days | 4FS+2 days | 0% | Frankie
10 | 2.1.2 | Nightly regression | 2 days | 9 | 0% | Avery