## Read me
FPGA Team Atlas: roadmap import template
1. Fill in the Tasks sheet, one row per task. Delete the grey example rows first.
2. Workstreams, Areas and Milestones are optional. Use them for IDs, descriptions, map hints and target dates. Anything the Tasks sheet names that isn't listed there is created for you.
3. IDs are optional. Leave one blank and the importer makes it: an area's tasks get the area's ID and a number, such as CI-04. Keep IDs short, with no spaces.
4. Depends on: the IDs or exact names of the tasks that must be finished first, separated by commas.
5. Status: Planned, In progress, In review, Done or Adopted. Done means published; Adopted means the team uses it routinely.
6. Estimate: a number of days. For hours or points, build the atlas with --estimate-unit hours (or points).
7. DAL: leave blank if every DAL needs the task, or list the ones that do, such as A, B.
8. Kind: template, checklist, guide, decision, setup, training or process.
9. Subtasks: one per line (Alt+Enter starts a new line in a cell). Start a line with [x] if it's done.
10. Any other column is kept as a property on each task note, so a Thread or Risk column isn't lost.
Then, from the repository folder:
python tools/import_roadmap.py roadmap.xlsx --dry-run (see what it understood; nothing is written)
python tools/import_roadmap.py roadmap.xlsx --fresh (replace the example roadmap with this one)
python tools/build_atlas.py (check the notes and build the page)

## Tasks
ID | Task | Workstream | Area | Status | Owner | Milestone | Estimate (days) | Depends on | DAL | Kind | Deliverable | Description | Subtasks
CH-01 | Team charter and principles | Ways of Working | Team Charter | Adopted | Lead | M1 | 3 |  |  | guide | library/guides/team-charter.md | What the team is for and how we work together. | [x] Draft the charter [x] Agree it with the team
CH-02 | Roles and responsibilities (RACI) | Ways of Working | Team Charter | In review | Lead | M1 | 2 | CH-01 |  | template |  | Who decides, who does the work, who is consulted.
CS-01 | VHDL coding standard refresh | Standards & Assurance | Coding Standard | In progress | Avery | M1 | 5 | CH-01 |  | guide |  | One standard everyone follows, with a reason for each rule. | [x] Gather the current rules [/] Draft v1 [ ] Review with the team

## Workstreams
ID | Workstream | Description | Map hint
WOW | Ways of Working | How we plan, track and share work, and how new people get up to speed. | west
STD | Standards & Assurance | Coding and design standards, reviews and verification, tailored by DAL.

## Areas
ID | Area | Workstream | Description
CH | Team Charter | WOW | What the team is for, who does what, and what done means.
CS | Coding Standard | STD | The VHDL, constraints, clock-domain-crossing and reset rules we design to.

## Milestones
ID | Milestone | Target date | Description
M1 | Foundations |  | Tracking tool decided; repository structure and team charter agreed.